## Sheet1
ID | Sprint | Theme | Role | Task | Reason | LOE | Time spent | Time Left | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Note
1 |  | Preliminary | Team | Planning |  | 2 | 3 | 0 | 1 | 1 | 1 | [15 empty] | Delete weeks to 10-12
2 |  | Documentation | Team | Team documentation |  | 2 | 2 | 0 |  | 1 | 1
3 |  | Preliminary | Customer | Wireframing |  | 3 | 3 | 0 |  | 1 | 1 | 1
4 |  | Preliminary | Customer | Design | Design of whole software | 2 | 2 | 0 |  |  |  | 2
5 |  | GUI | Customer/User/Admin | UI | Design of UI | 4 | 4 | 0 |  |  |  |  | 2 | 2
6 |  | Main | User/Admin | AppStart1 | Application shall start with user/ADMIN previous settings | 5 | 5 | 0 | [10 empty] | 2 |  |  | 1 |  |  | 2
7 |  | Main | User/Admin | AppStart2 | Application shall start with user/ADMIN Login screen | 3 | 3 | 0 | [7 empty] | 1 | 2
8 |  | Main | User/Admin | AppStart3 | Application shall allow user to ineract with embedded gui | 4 | 4 | 0 | [9 empty] | 2 | 2
9 |  | Main | User/Admin | AppStart4 | Application shall saves user/Admin settings | 8 | 8 | 0 | [10 empty] | 2 | 1 |  | 4 |  | 1
10 |  | Searchs | User/Admin | Search1 | System shall save search | 6 | 6 | 0 | [6 empty] | 3 | [5 empty] | 3
11 |  | Searchs | User/Admin | Search2 | System shall retrieve previous searchs | 5 | 5 | 0 | [5 empty] | 3 |  |  |  | 2
12 |  | Searchs | User/Admin | Search3 | System shall edit searchs | 4 | 4 | 0 | [7 empty] | 2 |  |  |  | 2
13 |  | Searchs | User/Admin | Search4 | System shall validate search before ploting | 6 | 6 | 0 | [6 empty] | 3 |  |  |  |  | 3
14 |  | User Authentication | User/Admin | UserAuthentication1 | Method shall log the user in | 5 | 4 | 0 |  |  |  |  | 1 |  | 2 |  | 1
15 |  | User Authentication | User/Admin | UserAuthentication2 | Method shall add the user if the user does not exist | 4 | 4 | 0 | [5 empty] | 2 |  |  |  | 2
16 |  | User Authentication | User/Admin | UserAuthentication3 | Method shall remove an user | 5 | 5 | 0 | [6 empty] | 2 |  | 1 |  | 2
17 |  | User Authentication | User/Admin | UserAuthentication4 | Method shall promote a user | 4 | 4 | 0 | [12 empty] | 2 |  |  | 2
18 |  | User Authentication | User/Admin | UserAuthentication5 | Method shall demote a user | 4 | 4 | 0 | [10 empty] | 1 |  |  | 2 |  |  | 1
19 |  | User Authentication | User/Admin | UserAuthentication6 | Method shall a new location | 6 | 6 | 0 | [5 empty] | 2 |  |  |  | 2 |  |  | 2
20 |  | User Authentication | User/Admin | UserAuthentication7 | Method shall remove a location from the database | 7 | 7 | 0 | [7 empty] | 2 |  |  | 2 |  | 2 |  |  | 1
21 | 6 |  | Team | Testing 1 | Error Checking | 3 | 3 | 0 | [9 empty] | 2 |  |  | 1
22 | 7 |  | Team | Testing 2 | Error Checking | 3 | 4 | 0 | [12 empty] | 4
23 | 8 |  | Team | Testing 3 | Error Checking | 2 | 2 | 0 | [16 empty] | 2
24 | 9 |  | Team | Testing 4 | Error Checking | 6 | 8 | 0 | [14 empty] | 1 | 4 | 3
25 | 10 |  | Team | Testing 5 | Error Checking | 3 | 3 | 0 | [7 empty] | 2 |  |  | 1
26 | 11 |  | Team | Testing 6 | Error Checking | 2 | 2 | 0 | [5 empty] | 1 |  |  |  | 1
27 | 12 |  | Team | Testing 7 | Error Checking | 2 | 2 | 0 | [5 empty] | 1 | [5 empty] | 1
28 | 13 |  | Team | Testing 8 | Error Checking | 4 | 4 | 0 | [6 empty] | 2 |  | 2
29 | 14 |  | Team | Testing 9 | Error Checking | 3 | 3 | 0 | [9 empty] | 2 |  |  | 1
30 | 15 |  | Team | Testing 10 | Error Checking | 2 | 2 | 0 | [10 empty] | 1 |  |  | 1
31 | 16 |  | Team | Testing 11 | Error Checking | 2 | 2 | 0 | [9 empty] | 1 |  |  |  |  | 1
32 | 17 |  | Team | Testing 12 | Error Checking | 3 | 3 | 0 | [11 empty] | 1 |  | 1 |  |  | 1
33 | 18 |  | Team | Testing 13 | Error Checking | 2 | 2 | 0 | [7 empty] | 1 | [6 empty] | 1
34 | 19 |  | Team | Testing 14 | Error Checking | 3 | 3 | 0 | [10 empty] | 1 |  | 1 |  |  | 1
35 | 20 |  | Team | Testing 15 | Error Checking | 4 | 4 | 0 | [8 empty] | 1 |  | 1 |  | 1 |  | 1
36 |  |  | Admin/User | Admin/User docs | Help documentations | 8 | 8 | 0 | [7 empty] | 2 | [5 empty] | 1 |  |  | 2 | 3
37 |  |  | Customer | Demo |  | 2 | 2 | 0 | [17 empty] | 2
18 | [6 empty] | 0 | 0
19 | [6 empty] | 0 | 0
20 | [6 empty] | 0 | 0
21 | [6 empty] | 0 | 0
22 | [6 empty] | 0 | 0
23 | [6 empty] | 0 | 0
24 | [6 empty] | 0 | 0
25 | [6 empty] | 0 | 0
26 | [6 empty] | 0 | 0
27 | [6 empty] | 0 | 0
28 | [6 empty] | 0 | 0
29 | [6 empty] | 0 | 0
30 | [6 empty] | 0 | 0
|  |  |  | TOTAL |  | 143 | 146 | 0 | 1 | 3 | 3 | 3 | 3 | 11 | 12 | 10 | 7 | 14 | 15 | 8 | 17 | 10 | 4 | 9 | 11 | 5
|  |  |  | Daily burnout |  | 64 |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4
|  |  |  | Total time left (from estimate) |  |  | Estimate | 143 | 138 | 134 | 129 | 125 | 120 | 116 | 111 | 107 | 102 | 98 | 94 | 89 | 85 | 81 | 77 | 72 | 68 | 64
|  |  |  | Total time left (from spent) |  |  | Burnout | 146 | 145 | 142 | 139 | 136 | 133 | 122 | 110 | 100 | 93 | 79 | 64 | 56 | 39 | 29 | 25 | 16 | 5 | 0