## Sheet1
ID | Sprint | Theme | Role | Task | Reason | LOE | Time spent | Time Left | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Note
1 |  | Preliminary | Team | Planning | Customer requires a desktop application program that maps shortest way between points | 2 | 2 | 0 | bar: 1 to 2
2 |  | Documentation | Team/Customer | Team documentation | Different documentation and specification needed to design application | 2 | 3 | 0 | bar: 1 to 3
3 |  | Preliminary | Customer | Wireframing | Application needs a basic layout to fit in input and output requirements | 3 | 3 | 0 | bar: 2 to 4
4 |  | Preliminary | Customer | Design | Needs overview application process to fulfill users and google earth requirement | 2 | 4 | 0 | bar: 1 to 4
5 |  | GUI | Customer/User/Admin | UI | Needs connection between the wirframing pages - how GUI will react to user actions | 4 | 4 | 0 | 2: 1; 3: 1; 4: 2
6 |  | Main | User/Admin | AppStart1 | Application shall start with user/ADMIN previous settings | 5 | 5 | 0 | 11: 2; 14: 1; 17: 2
7 |  | Main | User/Admin | AppStart2 | Application shall start with user/ADMIN Login screen | 3 | 3 | 0 | 8: 1; 9: 2
8 |  | Main | User/Admin | AppStart3 | Application shall allow user to ineract with embedded gui | 4 | 4 | 0 | 10: 2; 11: 2
9 |  | Main | User/Admin | AppStart4 | Application shall saves user/Admin settings | 8 | 8 | 0 | 11: 2; 12: 1; 14: 4; 16: 1
10 |  | Searchs | User/Admin | Search1 | System shall save search | 6 | 6 | 0 | 7: 3; 13: 3
11 |  | Searchs | User/Admin | Search2 | System shall retrieve previous searchs | 5 | 5 | 0 | 6: 3; 10: 2
12 |  | Searchs | User/Admin | Search3 | System shall edit searchs | 4 | 4 | 0 | 8: 2; 12: 2
13 |  | Searchs | User/Admin | Search4 | System shall validate search before ploting | 6 | 6 | 0 | 7: 3; 12: 3
14 |  | User Authentication | User/Admin | UserAuthentication1 | Method shall log the user in | 5 | 4 | 0 | 5: 1; 7: 2; 9: 1
15 |  | User Authentication | User/Admin | UserAuthentication2 | Method shall add the user if the user does not exist | 4 | 4 | 0 | 6: 2; 10: 2
16 |  | User Authentication | User/Admin | UserAuthentication3 | Method shall remove an user | 5 | 5 | 0 | 7: 2; 9: 1; 11: 2
17 |  | User Authentication | User/Admin | UserAuthentication4 | Method shall promote a user | 4 | 4 | 0 | 13: 2; 16: 2
18 |  | User Authentication | User/Admin | UserAuthentication5 | Method shall demote a user | 4 | 4 | 0 | 11: 1; 14: 2; 17: 1
19 |  | User Authentication | User/Admin | UserAuthentication6 | Method shall a new location | 6 | 6 | 0 | 6: 2; 10: 2; 13: 2
20 |  | User Authentication | User/Admin | UserAuthentication7 | Method shall remove a location from the database | 7 | 7 | 0 | 8: 2; 11: 2; 13: 2; 16: 1
21 |  | GUI | Admin/User | GUI1 | GUI that admin/user log in | 5 | 5 | 0 | 6: 1; 9: 1; 11: 1; 13: 2
22 |  | GUI | Admin | GUI2 | GUI that admin modify the location | 6 | 6 | 0 | 8: 2; 10: 1; 12: 3
23 |  | GUI | Admin | GUI3 | GUI that admin add the location | 5 | 5 | 0 | 9: 3; 11: 1; 12: 1
24 |  | GUI | Admin | GUI4 | GUI that allow user to switch to admin account | 7 | 7 | 0 | 12: 3; 14: 1; 15: 2; 16: 2
25 |  | GUI | User | GUI5 | GUI that allow user to select the locations | 5 | 5 | 0 | 13: 1; 15: 3; 16: 1
26 |  | GUI | User | GUI6 | GUI that allow user to sign up | 5 | 5 | 0
27 |  | SearchManager | User/Admin | SearchManager1 | Optimize Search path | 7 | 7 | 0 | 11: 3; 13: 2; 15: 2
28 |  | KMLManager | User/Admmin | KMLManager1 | Opens Google earth
29 |  | KMLManager | User/Admmin | KMLManager2 | Draws Shortest Path on Map
30 |  | KMLManager | User/Admmin | KMLManager3 | Validates Location
31 | 6 |  | Team | Testing 1 | Error Checking | 3 | 3 | 0 | 10: 2; 13: 1
32 | 7 |  | Team | Testing 2 | Error Checking | 3 | 4 | 0 | 13: 4
33 | 8 |  | Team | Testing 3 | Error Checking | 2 | 2 | 0 | 17: 2
34 | 9 |  | Team | Testing 4 | Error Checking | 6 | 8 | 0 | 15: 1; 16: 4; 17: 3
35 | 10 |  | Team | Testing 5 | Error Checking | 3 | 3 | 0 | 8: 2; 11: 1
36 | 11 |  | Team | Testing 6 | Error Checking | 2 | 2 | 0 | bar: 6; 10
37 | 12 |  | Team | Testing 7 | Error Checking | 2 | 2 | 0 | bar: 6; 12
38 | 13 |  | Team | Testing 8 | Error Checking | 4 | 4 | 0 | 7: 2; 9: 2
39 | 14 |  | Team | Testing 9 | Error Checking | 3 | 3 | 0 | 10: 2; 13: 1
40 | 15 |  | Team | Testing 10 | Error Checking | 2 | 2 | 0 | bar: 11; 14
41 | 16 |  | Team | Testing 11 | Error Checking | 2 | 2 | 0 | bar: 10; 15
42 | 17 |  | Team | Testing 12 | Error Checking | 3 | 3 | 0 | bar: 12; 14; 17
43 | 18 |  | Team | Testing 13 | Error Checking | 2 | 2 | 0 | bar: 8; 15
44 | 19 |  | Team | Testing 14 | Error Checking | 3 | 3 | 0 | bar: 11; 13; 16
45 | 20 |  | Team | Testing 15 | Error Checking | 4 | 4 | 0 | bar: 9; 11; 13; 15
46 | 21 |  | Team | Testing 16 | Error Checking | 4 | 4 | 0 | 10: 2; 12: 2
47 | 22 |  | Team | Testing 17 | Error Checking | 3 | 3 | 0 | 13: 1; 14: 2
48 | 23 |  | Team | Testing 18 | Error Checking | 2 | 2 | 0 | bar: 13; 15
49 | 24 |  | Team | Testing 19 | Error Checking | 2 | 2 | 0 | 14: 2
50 | 25 |  | Team | Testing 20 | Error Checking | 3 | 3 | 0 | 14: 2; 15: 1
51 | 26 |  | Team | Testing 21 | Error Checking | 3 | 3 | 0 | 15: 3
52 | 27 |  | Team | Testing 22 | Error Checking | 3 | 3 | 0 | 15: 3
52 | 28 |  | Team | Testing 23 | Error Checking | 3 | 3 | 0 | 15: 3
52 | 29 |  | Team | Testing 24 | Error Checking | 3 | 3 | 0 | 13: 3
52 | 30 |  | Team | Testing 25 | Error Checking | 3 | 3 | 0 | 15: 3
53 |  |  | Admin/User | Admin/User docs | Users/Admins need help documentation when using application | 8 | 8 | 2 | 14: 1; 17: 2; 18: 3
54 |  |  | Customer | Demo |  | 2 | 2 | 0 | 18: 2
18 | [6 empty] | 0 | 0
19 | [6 empty] | 0 | 0
20 | [6 empty] | 0 | 0
21 | [6 empty] | 0 | 0
22 | [6 empty] | 0 | 0
23 | [6 empty] | 0 | 0
24 | [6 empty] | 0 | 0
25 | [6 empty] | 0 | 0
26 | [6 empty] | 0 | 0
27 | [6 empty] | 0 | 0
28 | [6 empty] | 0 | 0
29 | [6 empty] | 0 | 0
30 | [6 empty] | 0 | 0
|  |  |  | TOTAL |  | 212 | 217 | 2 | 3 | 5 | 4 | 4 | 1 | 10 | 12 | 10 | 11 | 17 | 20 | 17 | 27 | 17 | 25 | 12 | 11 | 5
|  |  |  | Daily burnout |  | 133 |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4
|  |  |  | Total time left (from estimate) |  |  | Estimate | 212 | 207 | 203 | 198 | 194 | 189 | 185 | 180 | 176 | 171 | 167 | 163 | 158 | 154 | 150 | 146 | 141 | 137 | 133
|  |  |  | Total time left (from spent) |  |  | Burnout | 217 | 214 | 209 | 205 | 201 | 200 | 190 | 178 | 168 | 157 | 140 | 120 | 103 | 76 | 59 | 34 | 22 | 11 | 6