## Sheet1
ID | Sprint | Theme | Role | Task | Reason | LOE | Time spent | Time Left | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Note
1 |  | Preliminary | Team | Planning |  | 2 | 3 | 0 | [18 empty] | Delete weeks to 10-12 | bar: 1 to 3
2 |  | Documentation | Team | Team documentation |  | 2 | 2 | 0 | bar: 2 to 3
3 |  | Preliminary | Customer | Wireframing |  | 3 | 3 | 0 | bar: 2 to 4
4 |  | Preliminary | Customer | Design | Design of whole software | 2 | 2 | 0 | 4: 2
5 |  | GUI | Customer/User/Admin | UI | Design of UI | 4 | 4 | 0 | 5: 2; 6: 2
6 |  | Main | User/Admin | AppStart1 | Application shall start with user/ADMIN previous settings | 5 | 5 | 0 | 11: 2; 14: 1; 17: 2
7 |  | Main | User/Admin | AppStart2 | Application shall start with user/ADMIN Login screen | 3 | 3 | 0 | 8: 1; 9: 2
8 |  | Main | User/Admin | AppStart3 | Application shall allow user to ineract with embedded gui | 4 | 4 | 0 | 10: 2; 11: 2
9 |  | Main | User/Admin | AppStart4 | Application shall saves user/Admin settings | 8 | 8 | 0 | 11: 2; 12: 1; 14: 4; 16: 1
10 |  | Searchs | User/Admin | Search1 | System shall save search | 6 | 6 | 0 | 7: 3; 13: 3
11 |  | Searchs | User/Admin | Search2 | System shall retrieve previous searchs | 5 | 5 | 0 | 6: 3; 10: 2
12 |  | Searchs | User/Admin | Search3 | System shall edit searchs | 4 | 4 | 0 | 8: 2; 12: 2
13 |  | Searchs | User/Admin | Search4 | System shall validate search before ploting | 6 | 6 | 0 | 7: 3; 12: 3
14 | 6 |  | Team | Testing 1 | Error Checking | 3 | 3 | 0 | 10: 2; 13: 1
15 | 7 |  | Team | Testing 2 | Error Checking | 3 | 4 | 0 | 13: 4
16 | 8 |  | Team | Testing 3 | Error Checking | 2 | 2 | 0 | 17: 2
17 | 9 |  | Team | Testing 4 | Error Checking | 6 | 8 | 0 | 15: 1; 16: 4; 17: 3
18 | 10 |  | Team | Testing 5 | Error Checking | 3 | 3 | 0 | 8: 2; 11: 1
19 | 11 |  | Team | Testing 6 | Error Checking | 2 | 2 | 0 | bar: 6; 10
20 | 12 |  | Team | Testing 7 | Error Checking | 2 | 2 | 0 | bar: 6; 12
21 | 13 |  | Team | Testing 8 | Error Checking | 4 | 4 | 0 | 7: 2; 9: 2
18 |  |  | Admin/User | Admin/User docs | Help documentations | 8 | 8 | 0 | 8: 2; 14: 1; 17: 2; 18: 3
19 |  |  |  | Demo |  | 2 | 2 | 0 | 18: 2
18 | [6 empty] | 0 | 0
19 | [6 empty] | 0 | 0
20 | [6 empty] | 0 | 0
21 | [6 empty] | 0 | 0
22 | [6 empty] | 0 | 0
23 | [6 empty] | 0 | 0
24 | [6 empty] | 0 | 0
25 | [6 empty] | 0 | 0
26 | [6 empty] | 0 | 0
27 | [6 empty] | 0 | 0
28 | [6 empty] | 0 | 0
29 | [6 empty] | 0 | 0
30 | [6 empty] | 0 | 0
|  |  |  | TOTAL |  | 89 | 93 | 0 | 1 | 3 | 3 | 3 | 2 | 7 | 8 | 7 | 4 | 7 | 7 | 7 | 8 | 6 | 1 | 5 | 9 | 5
|  |  |  | Daily burnout |  | 10 |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4
|  |  |  | Total time left (from estimate) |  |  | Estimate | 89 | 84 | 80 | 75 | 71 | 66 | 62 | 57 | 53 | 48 | 44 | 40 | 35 | 31 | 27 | 23 | 18 | 14 | 10
|  |  |  | Total time left (from spent) |  |  | Burnout | 93 | 92 | 89 | 86 | 83 | 81 | 74 | 66 | 59 | 55 | 48 | 41 | 34 | 26 | 20 | 19 | 14 | 5 | 0