## Sheet1
ID | Sprint | Theme | Role | Task | Reason | LOE | Time spent | Time Left | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Note
|  |  |  | Planning |  | 2 | 3 | 0 | 1 | 1 | 1 | [15 empty] | Delete weeks to 10-12
|  |  |  | Team documentation |  | 2 | 2 | 0 |  | 1 | 1
|  |  |  | Wireframing |  | 3 | 3 | 0 |  | 1 | 1 | 1
|  |  |  | Design | Design of whole software | 2 | 2 | 0 |  |  |  | 2
|  |  |  | UI | Design of UI | 4 | 4 | 0 |  |  |  |  | 2 | 2
1 |  | Main |  | AppStart1 | Application starts with user/ADMIN previous settings | 5 | 5 | 0 | [10 empty] | 2 |  |  | 1 |  |  | 2
2 |  | Main |  | AppStart2 | Application starts with user/ADMIN Login screen | 3 | 3 | 0 | [7 empty] | 1 | 2
3 |  | Main |  | AppStart3 | Application allows user to ineract with embedded gui | 4 | 4 | 0 | [9 empty] | 2 | 2
4 |  | Main |  | AppStart4 | Application saves user/Admin settings | 8 | 8 | 0 | [10 empty] | 2 | 1 |  | 4 |  | 1
|  |  |  | Testing 1 |  | 3 | 3 | 0 | [9 empty] | 2 |  |  | 1
|  |  |  | Testing 2 |  | 3 | 4 | 0 | [12 empty] | 4
|  |  |  | Testing 3 |  | 2 | 2 | 0 | [16 empty] | 2
|  |  |  | Testing 4 |  | 6 | 8 | 0 | [14 empty] | 1 | 4 | 3
|  |  |  | Admin/User docs | Help documentations | 8 | 8 | 2 | [13 empty] | 1 |  |  | 2 | 3
|  |  |  | Demo |  | 2 | 2 | 1 | [17 empty] | 1
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
|  |  |  | TOTAL |  | 57 | 61 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 0 | 1 | 2 | 4 | 6 | 1 | 5 | 6 | 1 | 5 | 9 | 4
|  |  |  | Daily burnout |  | -22 |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4
|  |  |  | Total time left (from estimate) |  |  | Estimate | 57 | 52 | 48 | 43 | 39 | 34 | 30 | 25 | 21 | 16 | 12 | 8 | 3 | -1 | -5 | -9 | -14 | -18 | -22
|  |  |  | Total time left (from spent) |  |  | Burnout | 61 | 60 | 57 | 54 | 51 | 49 | 47 | 47 | 46 | 44 | 40 | 34 | 33 | 28 | 22 | 21 | 16 | 7 | 3